## Ark1
Task | Assigned to | Week 01 | [6 empty] | Week 02 | [6 empty] | Week 03 | [6 empty] | Week 04
US: Product contains pages |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Task: Wireframing | Visual designer | bar: Week 01 1
Task: Write content | Copywriter | bar: Week 01 1 to Week 01 2
Task: Design UI | UI Designer | bar: Week 01 2 to Week 01 3
Task: Design UX | UX Designer | bar: Week 01 2 to Week 01 3
Task: Write code | Front end developer | bar: Week 01 4 to Week 01 6
Task: Testing | Project Manager | bar: Week 01 7
Task: Present for customer | Project Manager | bar: Week 03 18 to Week 03 19
US: Manufacturing info page
Task: Wireframing | Visual designer | bar: Week 01 3
Task: Write content | Copywriter | bar: Week 01 3 to Week 01 4
Task: Design UI | UI Designer | bar: Week 01 4 to Week 01 5
Task: Design UX | UX Designer | bar: Week 01 4 to Week 01 5
Task: Write code | Front end developer | bar: Week 01 7 to Week 02 9
Task: Testing | Project Manager | bar: Week 02 10
Task: Present for customer | Project Manager | bar: Week 03 18 to Week 03 19
US: Chat function
Task: Wireframing | Visual designer | bar: Week 01 4
Task: Design UI | UI Designer | bar: Week 01 5 to Week 01 6
Task: Design UX | UX Designer | bar: Week 01 5 to Week 01 6
Task: Write code | Front end developer | bar: Week 02 11 to Week 02 13
Task: Testing | Project Manager | bar: Week 02 14
Task: Present for customer | Project Manager | bar: Week 03 18 to Week 03 19
US: Contact form
Task: Wireframing | Visual designer | bar: Week 01 5
Task: Design UI | UI Designer | bar: Week 01 7 to Week 02 8
Task: Design UX | UX Designer | bar: Week 01 7 to Week 02 8
Task: Write code | Front end developer | bar: Week 02 14 to Week 03 16
Task: Testing | Project Manager | bar: Week 03 17
Task: Present for customer | Project Manager | bar: Week 03 18 to Week 03 19
Deploy to production | Front end developer | bar: Week 03 20